## Bungalow Checklist
Dorothy Calhoun Property Maintenance Checklist
812 Meridian Street, Nashville, TN 37207 ¦ Managed by Carlos Moore
Updated: February 2026
Item | Area | Priority | Est. Cost | Assigned To | Status | Notes
Water heater replacement (14 years old) | Utility room | High | $1,100 to $1,400 | Carlos + Bob's Plumbing | Scheduled Oct 2026 | Same unit type as Bellevue house
Roof inspection, age unknown | Roof | High | $150 for inspection, repair TBD | Carlos (arrange) | Pending | Last known inspection was 2019
Front porch step repair, cracked concrete | Exterior | High | $400 to $600 | Raymond | Scheduled Nov 2026 visit | Trip hazard, priority for safety
HVAC service and filter replacement | HVAC | High | $120 | Carlos | Done Jan 2026 | Annual service, filter replaced
Kitchen faucet replacement, dripping | Kitchen | Medium | $180 to $250 | Carlos | Pending | Buying Delta faucet, will install Feb 2026
Bathroom exhaust fan repair, not running | Master bath | Medium | $80 to $120 | Carlos | Pending | Mold risk if not fixed
Exterior paint touch-up, front trim | Exterior | Medium | $200 materials | Raymond | Planned October 2026 | Wait for warmer weather
Gutter cleaning | Gutters | Medium | $150 | Carlos (arrange) | Pending, spring 2027 | Nashville Gutter Co.
Window weatherstripping replacement, 3 windows | Windows | Medium | $45 to $60 | Carlos | Pending | Drafty in January, she mentioned it
Backyard overgrowth clearance | Yard | Medium | $0 | Raymond | Planned Nov 2026 | Raymond brings tools when he visits
Smoke detector battery replacement, all units | Safety | High | $30 | Carlos | Done Jan 2026 | Done on January Saturday visit
Carbon monoxide detector replacement, expired | Safety | High | $45 | Carlos | Done Jan 2026 | Replaced same visit
Interior paint touch-up, hallway and bedroom | Interior | Low | $150 materials | Denise | Planned 2027 | She offered to do this when ready
Pest control, quarterly contract | Pest | Low | $89/quarter | Carlos (arrange) | Setting up contract | Will use Shield Pest, same as Bellevue
Doorbell replacement | Exterior | Low | $35 to $50 | Carlos | Pending | Ring unit also an option for camera
Dryer vent cleaning | Laundry | Medium | $100 | Carlos | Pending | Last cleaned unknown, fire risk
Attic insulation check | Attic | Low | $0 if DIY inspect | Raymond | Planned | Can check on next visit