## Committee Tasks
Calvary Hill Spring Fundraiser 2027 - Task Tracker
Updated: October 22, 2026 ¦ Chair: Carlos Moore
Task | Subcommittee | Owner | Status | Due Date | Notes
Confirm fellowship hall booking | Venue | Deacon Harold Briggs | Complete | October 15, 2026 | Confirmed with church office
Secure catering vendor | Food | Maria Moore | In progress | November 1, 2026 | Two vendors being compared
Finalize menu with caterer | Food | Maria Moore | Pending | November 15, 2026 | Southern buffet format
Collect baked goods sign-ups | Food | Sister Gloria Watkins | In progress | December 1, 2026 | Sheet posted in fellowship hall
Source silent auction items | Auction | Marcus Webb | In progress | November 15, 2026 | 12 of 20 items confirmed
Set auction item descriptions and min bids | Auction | Marcus Webb | Pending | December 1, 2026 | Will complete once items finalized
Print and distribute flyers | Marketing | DeShawn Avery | Pending | November 20, 2026 | Design draft due November 10
Set up social media event page | Marketing | DeShawn Avery | Complete | October 20, 2026 | Facebook and Instagram posted
Order printed programs | Marketing | DeShawn Avery | Pending | January 15, 2027 | Need final headcount first
Arrange decorations and centerpieces | Decorations | Cheryl Haynes | In progress | January 20, 2027 | Sourcing flowers and linens
Confirm sound system setup | AV | Brother Otis Freeman | Complete | October 22, 2026 | Using his personal equipment
Recruit parking volunteers | Logistics | Brother Kenneth Shaw | In progress | December 15, 2026 | Needs 4 more volunteers
Purchase raffle prizes | Raffle | Carlos Moore | Pending | December 15, 2026 | Gift cards from local businesses
Set up ticket sales page (Eventbrite) | Tickets | Carlos Moore | Complete | October 22, 2026 | Link sent to congregation
Confirm sponsor table placement | Sponsors | Monique Sheppard | Complete | October 22, 2026 | Nashville Music Credit Union confirmed
Train cash box volunteers | Finance | Brenda Coles | Pending | January 25, 2027 | Brief 30-minute walkthrough day before
Plan kids activity zone supplies | Logistics | Nathaniel Okonkwo | Pending | January 15, 2027 | Crafts and outdoor games
Finalize emcee script with Pastor | Program | Carlos Moore | Pending | January 20, 2027 | Pastor Whitfield leads opening and closing
Coordinate cleanup crew and breakdown | Logistics | Reggie Thomas | Pending | February 1, 2027 | Truck needed for equipment return
Submit final budget to church treasurer | Finance | Carlos Moore | Pending | November 30, 2026 | Waiting on catering quote