## Slide 1
Employee Wellness Program
Bellmark Industries | Full Rollout, January 2027
A healthier, more supported workforce
Voluntary platform for all 400 employees across three offices,
with mental health, fitness, and nutrition support built in.
Prepared by Carlos Moore, HR Director | Employee ID CM-2018-047

## Slide 2
Program at a Glance
What every employee gets, at no cost
400
Employees eligible
8
Free counseling sessions / yr
4.2
Pilot rating out of 5
$0
Employee cost
• Mental health and EAP. Native employee assistance with eight free sessions per person each year.
• Fitness and activity tracking. Syncs with common wearables and phone apps, no hardware required.
• Nutrition guidance. Weekly content and a dietitian question and answer feature.
• One sign-on. Access through the company single sign-on, eligibility synced from records.

## Slide 3
Vendor Evaluation
Weighted scores across nine criteria, September 2025
Chart: 
| HealthPath Solutions | WellTrack Inc. | VitalMax Health
Weighted score | 92 | 78 | 68
• HealthPath selected. Highest score on native EAP and admin reporting.
• Best pilot rating. 4.2 of 5 versus 3.8 and 3.5 for the others.
• Strong references. Three manufacturing HR directors, all positive.
• Decision locked. Contract signed November 2025.

## Slide 4
Rollout Plan
Phase two milestones, owners, and target dates
Milestone | Owner | Target | Status
Contract and privacy addendum signed | CM and Legal | December 2025 | Done
Records and single sign-on integration | IT and CM | October 2026 | In progress
Employee communication plan | Carlos Moore | October 2026 | In progress
Manager training sessions | Carlos Moore | November 2026 | Pending
All hands announcement | Carlos Moore | November 2026 | Pending
Program live for all employees | CM and HealthPath | January 2027 | Scheduled

## Slide 5
Pilot Results
How the thirty person pilot rated each pillar
Chart: 
| Mental health | Fitness tracking | Nutrition | Admin reporting
Satisfaction | 94 | 88 | 86 | 92

## Slide 6
Healthier people, stronger company.
Next: finalize integration and the communication plan through October 2026,
manager training in November, and launch to all employees in January 2027.
Carlos Moore | carlos.moore@Finthesiss.ai | (615) 555-0117