# Bellmark Industries

# Employee Wellness Program Rollout Checklist

Project Lead: Carlos Moore, HR Director | Employee ID: CM-2018-047

Vendor: HealthPath Solutions | Program Launch Target: January 2027

## Program Overview

Voluntary wellness platform for all 400 Bellmark employees across three offices.

Features: mental health resources, fitness tracking, nutrition guidance, and EAP integration.

Pilot group (30 employees) completed evaluation September 2025. Results positive.

Full rollout planned for January 2027 following benefits enrollment cycle.

## Phase 1 - Vendor Selection (Complete)

| Task | Timeline | Status | Owner |
| --- | --- | --- | --- |
| RFP distributed to five vendors | March 2025 | Done | CM |
| Vendor demos completed | May 2025 | Done | CM |
| Pilot evaluation with 30 employees | July 2025 to September 2025 | Done | CM and HR team |
| Contract with HealthPath Solutions signed | November 2025 | Done | CM and Wanda Giles |
| Legal review and data privacy addendum signed | December 2025 | Done | Legal |
| DocuSign routing of final agreements | January 2026 | Done | CM |

## Phase 2 - Launch Preparation (In Progress)

| Task | Target Date | Status | Owner |
| --- | --- | --- | --- |
| IT integration with BambooHR and Single Sign-On | October 2026 | In progress | IT and CM |
| Employee communication plan drafted | October 2026 | In progress | CM |
| Manager training sessions scheduled | November 2026 | Pending | CM |
| Benefits enrollment materials updated to include wellness benefit | October 2026 | In progress | CM |
| Enrollment confirmation emails via Mailgun tested | October 2026 | Pending | IT |
| Legal review of employee data handling disclosure | October 2026 | Pending | Legal |
| Pilot participant feedback survey distributed | October 2026 | Pending | CM |
| All-hands communication email drafted for Wanda approval | November 2026 | Pending | CM |

## Phase 3 - Post-Launch (Upcoming)

30-day check-in with HealthPath implementation manager (February 2027).

First participation report to Wanda Giles (February 2027).

90-day engagement metrics review and vendor scorecard (April 2027).

Mid-year wellness program assessment for DEI committee (July 2027).

Annual report and renewal decision (November 2027).

## Notes

Confidential. Do not distribute outside HR leadership without approval.

Questions: carlos.moore@Finthesiss.ai or (615) 555-0117