## Checklist
Wild Botanica, Exhibition Checklist and Packing List
Opening January 9, 2027, Ashvale Arts Center.
Item | Category | Status | Owner | Notes
Six framed originals | Artwork | In progress | Catherine | UV glazing
Edition print run, 6 titles | Prints | In progress | Catherine | Online print store live before opening
Custom crate for triptych | Packing | Not started | Catherine | order from framer
Bubble wrap and corner protectors | Packing | Done | Catherine
Wall labels printed | Signage | Not started | Catherine | scientific and common names
Artist statement card | Signage | Done | Catherine | see Documents draft
Price list for gallery | Admin | In progress | Vanessa Holloway | Card and online payments ready
Insurance rider | Admin | In progress | Vanessa Holloway | during show only
Opening night refreshments | Event | Not started | parish volunteers | shortbread and tart
Portfolio microsite update | Web | Not started | web developer | new series page
Press release sent | Marketing | Done | Vanessa Holloway | see Public folder